## Maintenance
CHANGE ORDER FORMAT
(Lump Sum)
CHANGE ORDER No. 2
Project Name: Campus Services Warehouse - Maintenance
Project Number: 0011-2016 / Contract No.: 0862-16
1. Submission of this Change Order for consideration was authorized by letter from the Owner, dated September 8, 2016,
Incumbrance Record No.17728-2016.
2. The changes hereinafter described are applicable to the Contract for the construction of the above-referenced
Project and amend the Contract Documents.
3. Description of Change: Additional work due to sub contractor changes related to silo demolition,
removal of high fructose powder in the silo, additional oversigt associated with this work.
Fire line modifications, safety striping and lettering, masonry repairs
4. This Change Order is deemed necessary and originated with the Owner
5. This Change Order is necessary to: Remove a silo and its contents,
ensure the space is weather proof and complies to safety codes
6. The amount of the Change Order was determined by: Negotiation
7. A memorandum is attached showing cost breakdown of labor and materials by unit and quantities as prepared
by the Contractor and checked by the Contract Compliance Specialist and Program Manager (if any).
8. We have verified the quantity and quality of all materials shown on the memorandum. We have verified that all
prices are reasonable and do not exceed current costs for like services or materials, and we have verified that the quality of
the materials meets the requirements of the Contract Documents.
9. The contractor shall be allowed 25 additional calendar days for completion. The Material Completion and
Occupancy Date is: August 26th, 2016 .
10. SUMMARY (ADJUSTED CONTRACT PRICE)
Original Contract Sum. | 257354
CHANGE ORDER NO. ADDITIONS DEDUCTIONS
1
Net additions and deductions of all approved Change Orders | 36142
Total adjusted contract price prior to this Change Order. | 293496
The Contract Sum shall be (increase) (decrease)by
on account of this change. | 78087
Total percentage of change orders 3.29573424513683 %
TOTAL CURRENT ADJUSTED CONTRACT PRICE | 371583
11. The payment and extension of time, if any, provided by this Change Order constitutes compensation in full to the
Contractor and its Subcontractors, Suppliers, and Trade Contractors for all costs and markups, directly and indirectly
attributable to the changes ordered herein, and for all delays or time related costs thereto and for any acceleration costs for
performance of changes within the time stated and to be completed by the Material Completion and Occupancy Date and
for any claims related thereto against the Owner and the Design Professional, and design consultants.
APPROVED AND AGREED BY CONTRACTOR: RECOMMENDED FOR OWNER'S ACCEPTANCE
Legal Name of Firm Design Professional: Legal Name of Firm
By:____________________________________ By:
____________________________________ ____________________________________________
(Print Name/Title) (Print Name/Title)
Date approved by Contractor: ____________ Date approved by Design Professional:
APPROVED AND AGREED BY USING AGENCY: APPROVED AND AGREED BY OWNER:
GEORGIA INSTITUTE OF TECHNOLOGY BOARD OF REGRENTS OF THE UNIVERSITY
By: ______________________________________ By: ___________________________________
Charles G. Rhode, Vice President Facilities Management
(Print Name/Title) (Print Name/Title)
Date approved by Using Agency: ______________ Date approved by Owner:

## Capital
CHANGE ORDER FORMAT
(Lump Sum)
CHANGE ORDER No. ___
Project Name:
| Building Number/Name: |  |  |  | Project Number:
Contract Number:
1. | Submission of this Change Order for consideration was authorized by the Owner on |  |  |  | 2016-09-09
Incumbrance Record No.__________________ (if BOR project)
2. | The changes hereinafter described are applicable to the Contract for the construction of the above-referenced
Project and amend the Contract Documents.
3. | Description of Change:
4. | This Change Order is deemed necessary and originated with the
5. | This Change Order is necessary to:
6. | The amount of the Change Order was determined by:
7. | A memorandum is attached showing cost breakdown of labor and materials by unit and quantities as prepared
by the Contractor and checked by the Contract Compliance Specialist and Program Manager (if any).
8. | We have verified the quantity and quality of all materials shown on the memorandum. We have verified that all
prices are reasonable and do not exceed current costs for like services or materials, and we have verified that the quality of
the materials meets the requirements of the Contract Documents.
9. | The contractor shall be allowed ___ additional calendar days for completion. The Material Completion and
Occupancy Date is:
10. | SUMMARY (ADJUSTED CONTRACT PRICE)
|  | Original Contract Amount |  |  | 0
|  | CHANGE ORDER NO. | ADDITIONS | DEDUCTIONS
|  | Net additions and deductions of all approved Change Orders |  |  | 0
|  | Total adjusted contract price prior to this Change Order. |  |  | 0
The Contract Sum shall be (increase) (decrease)by
|  | on account of this change. |  |  | 0
|  | Total percentage of change orders % |  |  | 0.00%
| TOTAL CURRENT ADJUSTED CONTRACT PRICE |  |  |  | 0
11. | The payment and extension of time, if any, provided by this Change Order constitutes compensation in full to the
Contractor and its Subcontractors, Suppliers, and Trade Contractors for all costs and markups, directly and indirectly
attributable to the changes ordered herein, and for all delays or time related costs thereto and for any acceleration costs for
performance of changes within the time stated and to be completed by the Material Completion and Occupancy Date and
for any claims related thereto against the Owner and the Design Professional, and design consultants.
| APPROVED AND AGREED BY CONTRACTOR: |  |  | RECOMMENDED FOR OWNER'S ACCEPTANCE
| Legal Name of Firm |  |  | Design Professional: Legal Name of Firm
| By:______________________________ |  |  | By: _________________________________________
| ____________________________________ |  |  | ____________________________________________
| (Print Name/Title) |  |  | (Print Name/Title)
| Date approved by Contractor: ____________ |  |  | Date approved by Design Professional:___________
| APPROVED AND AGREED BY USING AGENCY: |  |  | APPROVED AND AGREED BY OWNER:
| GEORGIA INSTITUTE OF TECHNOLOGY |  |  | BOARD OF REGRENTS OF THE UNIVERSITY
| By: _________________________________ |  |  | By: ___________________________________
Charles G. Rhode, Vice President Facilities Management
| (Print Name/Title) |  |  | (Print Name/Title)
| Date approved by Using Agency: ______________ |  |  | Date approved by Owner:__________________________

## Data
Origination List
Design Professional
Owner
Contractor